## Sheet1
ID | Title | Epic | Priority (MoSCoW) | Status | User Story | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate
1 | Data Collection | Web Scraper Development | Must | In Progress | As a developer, I want to collect job postings from Naukri.com to build a dataset for analysis. | 1. Extract job titles, descriptions, company names, and contact details. 2. Store data in a structured format (CSV/DB). | Web scraper that collects structured job listing data. Supports scheduling for regular updates. | Efficient data extraction without overloading the website. | 7 days
2 | Data Cleaning & Preprocessing | Data Preparation | Must | Pending | As a data scientist, I want to clean and preprocess job listing data to remove inconsistencies. | 1. Remove duplicate and incomplete listings. 2. Normalize text data for analysis. | Text preprocessing: tokenization, stopword removal, and stemming. Handle missing values. | Scalable processing for large datasets. | 5 days
3 | Model Selection | AI Model Development | Should | Pending | As a data scientist, I want to evaluate different ML/NLP models to find the best for fake job detection. | 1. Compare performance of multiple models (SVM, BERT, LSTM, etc.). 2. Select the best model based on accuracy. | Implement multiple AI models and log performance metrics. | Optimize model training to balance accuracy and speed. | 10 days
4 | Model Training & Optimization | AI Model Development | Must | Pending | As a developer, I want to train the selected model on collected job listings to detect fraudulent ones. | 1. Train model with labeled job listings. 2. Optimize accuracy to at least 85%. | Fine-tune model hyperparameters. Use TF-IDF or word embeddings for NLP. | Efficient model training using GPU acceleration. | 12 days
5 | Model Deployment | Backend Development | Must | Pending | As a developer, I want to deploy the trained AI model as an API for real-time inference. | 1. Model can receive job listings and classify them as real/fake. 2. API response time <500ms. | REST API with endpoints for job listing classification. Supports batch processing. | Scalable cloud-based deployment. Low latency API. | 7 days
6 | Chrome Extension UI | Chrome Extension Development | Must | Pending | As a user, I want an easy-to-use Chrome extension UI to see alerts for fake job listings. | 1. UI displays job listing details with warnings. 2. Simple and intuitive interface. | Browser-based UI with warning labels. Tooltip for detailed analysis. | Lightweight and non-intrusive design. | 7 days
7 | AI Model Integration | Chrome Extension Development | Must | Pending | As a developer, I want to integrate the AI model with the Chrome extension for real-time detection. | 1. Extension can send job listings to API and display warnings. 2. Works on job listings in real time. | Connect extension frontend to backend API. Supports automated detection. | Secure API communication. Works efficiently in real time. | 10 days
8 | Alert & Warning System | Chrome Extension Development | Should | Pending | As a user, I want alerts when a job listing is classified as fraudulent. | 1. Displays a warning icon on fraudulent job postings. 2. Shows confidence score. | Red/green indicators for fraudulent vs. genuine listings. Detailed explanation available. | Low resource usage to avoid slowing down browsing. | 5 days
9 | Testing & Debugging | Testing & Deployment | Must | Pending | As a QA engineer, I want to test the system for accuracy and performance. | 1. Model is evaluated with real-world job postings. 2. False positive rate <10%. | Implement unit, integration, and end-to-end testing. | Ensure stability under heavy usage. | 7 days
10 | Deployment & Documentation | Deployment | Must | Backlog | As a developer, I want to publish the Chrome extension and provide user documentation. | 1. Chrome extension is available in the Chrome Web Store. 2. Clear setup guide for users. | Hosted on the Chrome Web Store. Includes troubleshooting guide. | Lightweight and easy installation. | 5 days